CoBo Tasks & Milestones

(Time estimates assume 50% effort of NU & implementation using development kit)

- CoBo Documentation

  - Complete 1st draft by April 30, 2009

  - Complete 2nd draft by July 1, 2009

  - Complete prototype 1 draft by October 1, 2009

  - Complete prototype 2 by February 1, 2010

  - Final version by May 1, 2010

- Firmware Development

  - Microprocessor memory space

    - Must be defined to allow software development to begin

    - Complete by April 21st

  - High speed data readout

    - Implementation of segmented pipeline (1wk)

    - Zero suppression (1wk)

    - Built in flexibility for additional pipeline steps

      - Zip compression (future)

      - Peak fitting algorithms (future)

      - Etc

  - Double buffer SD-RAM (1 month code & test)

    - Firmware interface with SD chip

    - Switching mechanism between chips

  - Packet creation (1 month code; req e for testing)

    - Implement TCP packets in firmware

      - Checksum

      - Packet size definition

    - Define substructure of packet

      - Header

      - Data ordering

  - Microprocessor software (schedule assumes work completed at non-MSU site w/ 1 month implementation in CoBo)

    - Confirm selection of OS

      - (C real time OS II

      - other?

      - Define by April 21, 2009

    - Implement debug feature

    - Reading & slow controls packets

    - Acknowledge high speed data transmission

    - Monitoring features

      - Voltage

      - Temperature

      - Current

      - Etc

    - Fast/slow controls

      - Needs requirements defined

- Hardware

  - Component Selection (completed by June 1, 2009)

    - FPGA

      - Delay finalizing until after prototype 1

      - Use 1136 pin Virtex5 line

      - Confirm selection w/ Shebli

    - Clock Chip

      - Determine number required

        - 1 for SCA write (freq depends on expt)

        - Do separate clocks need to be sent to the ADC and the SCA read? (freq = 25 MHz)

      - Discuss selection w/ Gilles

    - RAM chip

      - Confirm chip selected is appropriate.

      - Is extra RAM required for processor or is enough block memory available already?

      - Need to know from software group the size of the compiled software.

      - Discuss w/ Shebli

    - ROM chip

      - Two required

      - Use ROM from Xilinx that matches FPGA

      - Confirm selection with software group

      - Discuss w/ Shebli

    - Ethernet interface

      - If using 1 Gbit Ethernet copy from development kit

      - If using 10 Gbit Ethernet research required

      - Need discussion among engineers

  - Interface Definition (completed by July 1, 2009)

    - Mutant

      - Add sync signal

      - Confirm connectors w/ Gilles

    - ASAD

      - Confirm slow controls & data transmitted of same cable

      - Confirm connectors w/ Jerome

    - Switch

      - Who will be handling this?

  - Board Schematics (4wks)

  - Board Layout (8wks)

  - Finalize number of CoBos to be produced (April 1, 2010)